AWS First Cloud AI Journey – Project Plan

Serverless Student Cloud Team – FPT University – Server-less Student Management System

[2025-12-07]

Table of Contents

1	BACKGROUND and motivation	3

1.1	executive summary	3

1.2	PROJECT SUCCESS CRITERIA	3

1.3	Assumptions	4

2	SOLUTION ARCHITECTURE / ARCHITECTURAL DIAGRAM	4

2.1	Technical Architecture Diagram	4

2.2	Technical Plan	5

2.3	Project Plan	5

2.4	Security Considerations	5

3	Activities AND Deliverables	6

3.1	Activities and deliverables	6

3.2	OUT OF SCOPE	7

3.3	PATH TO PRODUCTION	7

4	EXPECTED AWS COST BREAKDOWN BY SERVICES	8

5	TEAM	6

- BACKGROUND and motivation

  - executive summary

The Serverless Student Management System is a student management platform built entirely on AWS Serverless technologies. The goal is to deliver a modern, cost-efficient, scalable solution for managing students, courses, assignments, and grades using AWS services such as API Gateway, Lambda, Dynamo Db, Cognito, and Amplify.

Customer background:

This project is designed as an internal application used within an educational environment. The system is intended for administrators, teachers, and students who require a centralized platform for managing academic information such as students, courses, grades, and assignments.

Business & technical objectives:

- Build a truly 90% serverless student management application

- Optimize operational cost (under $20/month)

- Fully implement CI/CD from GitLab → CodePipeline

- Build a complete full-stack system (React/Amplify + API Gateway + Lambda + DynamoDB)

Use cases:

- Student management (CRUD, search, import)

- Course, assignment, and grade management

- Admin/teacher dashboard

- Authentication & authorization with Cognito

Professional services delivered:

- Serverless architecture design following AWS Well-Architected Framework

- Backend, frontend, CI/CD implementation

  - PROJECT SUCCESS CRITERIA

- One API Gateway with resources `/` and `/{proxy+}` (proxy resource), using ANY and OPTIONS methods, proxy integration forwards all requests to 1 Lambda Function.

- 1 AWS Lambda functions with >80% unit test coverage

- 5 fully functional modules: Students, Courses, Grades, Assignments, Dashboard

- React/TypeScript frontend deployed via Amplify with 15+ pages

- API response time < 500ms

- Uptime ≥ 99%

- CI/CD automated from GitLab → CodeBuild → CodeDeploy/Amplify → Production

- Infrastructure cost maintained < $20/month

  - Assumptions

- AWS Free Tier is used throughout the project

- All environments use serverless services only (no EC2)

- Active users < 200 per month

- API calls < 500k/month

- DynamoDB data volume < 10GB

- Team has basic knowledge of React, Java, and AWS Cloud

- Services like Route53 domain and WAF may incur costs but are included in scope

- SOLUTION ARCHITECTURE / ARCHITECTURAL DIAGRAM

  - Technical Architecture Diagram

  - Technical Plan

The system is built using AWS Serverless Architecture, consisting of 5 major layers:

- Edge Layer:Route53, CloudFront, WAF

- Frontend Layer: Amplify, Cognito

- Backend Layer: API Gateway, Lambda, DynamoDB

- Monitoring: CloudWatch

- CI/CD: GitLab, CodePipeline, CodeBuild, CodeDeploy, S3

Main API groups:

- `/students/` (CRUD, search, import/export)

- `/courses/`

- `/grades/`

- `/assignments/`

- `/auth/`

  - Project Plan

The project will be implemented in 5 weeks:

- Week 1: AWS setup, IaC, DynamoDB, Cognito, Git repository

- Week 2: Backend & Frontend Phase 1 (Lambda + API Gateway + basic UI)

- Week 3: Backend & Frontend Phase 2 (15+ pages, integration test, CloudFront + WAF)

- Week 4: CI/CD (CodeBuild, CodeDeploy, CodePipeline)

- Week 5: Testing, optimization, documentation, demo

  - Security Considerations

- IAM least privilege

- Cognito User Pool + JWT authentication

- API Gateway throttling (rate limiting)

- WAF rules (SQLi/XSS, IP block, rate limiting)

- DynamoDB encryption

- CloudWatch alarms

- Activities AND Deliverables

  - Activities and deliverables

| Project Phase | Timeline | Activities | Deliverables/Milestones | Total man-day |
| --- | --- | --- | --- | --- |
| Assessment | Week 1 | - Setup AWS account, IAM, billing alerts - Create DynamoDB + GSI tables - Configure Cognito user groups and groups - Design detailed architecture, sequence diagrams - Initialize IaC structure (CDK/CloudFormation), Git repo | - AWS foundation complete - DynamoDB + Cognito operational - Architecture documentation + workflow diagrams - Repo & IaC ready | 28 man-day |
| Setup base infrastructure | Week 2 | - Backend: build Lambda (Students, Courses, Grades, Assignments, Auth) - Setup API Gateway endpoints - Unit tests 80%+ - Frontend: implement Amplify, routing, UI core layout - Integrate state management, API client | - Lambda functions working - API Gateway stable - Frontend base UI complete - Unit test passed1 | 35 man-day |
| Setup component 1 | Week 3 | - Backend: automatic workflow integration, integration testing - Frontend: build 15+ pages (Students, Courses, Grades, Assignments) - CloudFront connection – Route53 – WAF – SSL/TLS - End-to-end integration FE ↔ BE | - Complete backend workflow - Full operational management page - Domain + CDN + WAF + HTTPS running smoothly - E2E test passed | 35 man-day |
| Setup component 2 (CI/CD) | Week 4 | - Configure CodeBuild for FE & BE - Set up CodePipeline (source → build → deploy) - Configure CodeDeploy to deploy backend & frontend - Test the entire pipeline | - Complete CI/CD pipeline - Automatic build & deploy - Test pipeline report | 25 man-day] |
| Testing & Golive | Week 5 | - E2E testing, edge cases, load testing 100+ users - Performance optimization (Lambda, DynamoDB, CloudFront) - Standardization of technical documentation, user manual - Demo preparation and testing | - Load test report - Optimized and stable system - Full documentation (architecture, API, deployment guide) - Complete demo | 35 man-day |

  - OUT OF SCOPE

- Mobile Applications (iOS/Android)

- AI recommender system / ML scoring

- Multi-region failover

- Enterprise SSO (SAML, OIDC)

  - PATH TO PRODUCTION

- Commit code → GitLab

- CodePipeline (source stage)

- CodeBuild (frontend & backend build)

- CodeDeploy (Lambda deployment + Amplify)

- CloudWatch (logs & monitoring)

- DNS routing via Route53 + CloudFront

- EXPECTED AWS COST BREAKDOWN BY SERVICES

AWS monthly pricing calculator

| Service | Monthly Estimate | Notes |
| --- | --- | --- |
| API Gateway | ~$3.8 | 100k–500k requests |
| Lambda | ~$0.5 | Free Tier includes 1M requests |
| DynamoDB | ~$1 | <10GB data |
| Cognito | $0 | <10k MAU |
| S3 | ~$0.13 | Artifacts & hosting |
| CloudWatch | ~$4 | Logs & metrics |
| Amplify | ~$1 | Frontend hosting |
| Route53 | ~$1 | DNS hosted zone |
| WAF | ~$7 | Web ACL |
| CodeBuild | ~$0.9 | ~100 build minutes |
| CodePipeline | ~$1 | 1 pipeline |
| CloudFront | ~$1 | CDN traffic |

Total Estimated Cost: ~ $7 – $20 / month

For 3 months: ~$21 – $60 (can be reduced to $15–30 with Free Tier).

- TEAM

Partner Project Team

| Name | Title | Role | Email / Contact Info |
| --- | --- | --- | --- |
| Nguyễn Hoàng Nam | FCJ Cloud Intern | Project Lead/ Backe-End | namnhse182076@fpt.edu.vn |
| Phạm Bảo Phi | FCJ Cloud Intern | Full Stack | phipbse185046@fpt.edu.vn |
| Nguyễn Nhật Kim Ngân | FCJ Cloud Intern | Frontend /BA | ngannnkse182088@fpt.edu.vn |
| Đặng Huy Hoàng | FCJ Cloud Intern | Back-End/DevOps | hoangdhse184661@fpt.edu.vn |
| Lâm Thanh Phúc | FCJ Cloud Intern | Back-End/DevOps | phucltse184678@fpt.edu.vn |